Yes — this page explains how your manager decides what kind of award to recommend, and what evidence they need.

## Main idea

There are two types of Achievement Award:

### 1. Consolidated increase

This is a permanent salary increase.

It is used when your exceptional contribution:

- has been sustained over time

- is consistent

- is clearly beyond your normal role

- has lasting or strategic impact

### 2. One-off payment

This is a single payment, not a permanent salary rise.

It is used when your contribution:

- was linked to a specific project or period

- was exceptional but time-limited

- does not represent ongoing change

- or when you are already near the top of your grade

## What this means for you

Your manager is supposed to ask:

### Is this achievement:

- ongoing and sustained?
→ then maybe consolidated increase

or

- specific and one-off?
→ then maybe one-off payment

## Very important points from the guidance

### A. It must be beyond normal job expectations

They are very clear:

- the achievement must be in addition to the usual expectations of the role

- not just doing your job well

So your evidence must show:

- why your work was unusual

- why it was exceptional

- why it exceeded what would normally be expected at your grade

### B. Your manager writes the supporting statement

The manager must submit:

- a specific

- detailed

- easy-to-understand
statement explaining your achievements

So your job is likely to:

- help your manager by giving them clear bullet points

- explain impact in simple language

- show evidence

### C. Salary position matters

Even if someone is exceptional, Imperial also looks at where they already sit in their pay grade.

If someone is:

- lower in the grade → a consolidated increase may be easier to justify

- near the top / upper quartile → a one-off payment is more likely

- at maximum → one-off only

So two people with similar achievement may get different award types depending on salary position.

### D. Team awards are always one-off

If the achievement was as part of a team, it would usually be a one-off payment, not a permanent increase.

### E. Externally funded staff can still be considered

This again confirms:

- staff funded by grants like European Commission / Marie Curie are not automatically excluded

- but the award cannot be charged to the grant

- the department must pay from its own internal budget

So your department saying you are eligible still makes sense.

## How to interpret this for your own case

If your achievements are things like:

- setting up a robot platform very fast

- developing simulation infrastructure early

- producing outputs ahead of schedule

- contributing beyond your own project

- doing this consistently across the year

then your manager may argue for a consolidated award
if they believe it shows sustained exceptional performance.

If instead the strongest case is:

- one particularly impressive project

- one unusually successful result

- one intense period of exceptional work

then it may be framed as a one-off award.

## Simple decision rule

### Likely consolidated

if you can show:

- exceptional performance over much of the review period

- continuing high-level contribution

- broader or lasting impact

- increased autonomy/leadership beyond role expectations

### Likely one-off

if you can show:

- one major technical success

- one important project delivered exceptionally well

- one short but outstanding contribution

- or you are already near the top of your salary grade

## What your manager needs from you

You should probably give your manager 3–5 short bullet points like this:

- What I did

- Why this was beyond normal expectations

- What impact it had

- Whether it was sustained or one-off

- Any evidence: deadlines, outputs, papers, systems built, collaborations, student support, feedback

## Example using your situation

### If you want to frame it as sustained

Since joining, I have consistently delivered at a level beyond the expected pace for the role. Within six months, I established both the robotic platform and simulation environment, enabling earlier-than-planned experimentation. I have continued to build on this through sustained technical delivery, independent problem-solving, and broader research contributions to the group.

### If you want to frame it as one-off

I delivered an exceptional piece of work by establishing the robotic and simulation infrastructure within six months, significantly accelerating the project and enabling early research outputs beyond the original timeline.

## What this page is really saying in plain English

It says:

- Managers decide who to recommend

- They must use evidence

- The case must show work above normal expectations

- The award can be either:

  - permanent increase for sustained exceptional work

  - one-off payment for a specific exceptional contribution

- If you are grant-funded, the department must fund it internally

## What you should do next

You should prepare a short note for your manager with:

### Section 1: Sustained achievements

Things you have done consistently over the year

### Section 2: One-off standout achievements

A major result/project completed exceptionally well

### Section 3: Impact

How your work helped:

- research

- lab/group

- department

- Imperial

If you want, I can now help you do one of these:

- turn your achievements into a manager-ready bullet list

- write a 300-word supporting statement

- decide whether your case sounds more like consolidated or one-off

If you send me your achievements in rough form, I’ll rewrite them clearly.

## Revised work packages aligned to the present work

Below is a modified WP structure that better matches your current research direction while still remaining clearly connected to the original proposal.

### Overall note

The original proposal was centered on CASREx / FReSCMA / exosuit stiffness modulation for rehabilitation, with a timeline built around actuator development, modelling, control, and pilot testing.
Your present work has evolved into a broader and stronger pipeline consisting of:

- manipulator + exosuit hardware,

- digital twins in PyDrake and Isaac Sim,

- rail-based ball-in-cup human experiment,

- tele-impedance / stiffness transfer framework,

- musculoskeletal modelling and endpoint stiffness estimation,

- synthetic EMG generation,

- ethics preparation and planned human testing.

So the best strategy is not to abandon the proposal structure entirely, but to reinterpret and update the WPs so they reflect the current work.

# Modified Work Package Structure

## WP1 — Hardware Platform Development and Experimental Setup

Period: Mo1–8
Objective: Develop the physical research platform for stiffness modulation and human-inspired manipulation experiments.

### Tasks

- T1.1 Build manipulator hardware platform.

- T1.2 Build exosuit/stiffness-modulation hardware.

- T1.3 Develop the two-rail ball-in-cup human experimental platform.

- T1.4 Integrate sensing hardware (force/torque, camera, EMG, rail position).

- T1.5 Perform initial hardware validation and bench testing.

### Deliverables

- D1.1 Manipulator hardware platform completed.

- D1.2 Exosuit stiffness-modulation hardware completed.

- D1.3 Human rail-based ball-in-cup platform designed and assembled.

- D1.4 Sensor integration and calibration framework.

- D1.5 Initial hardware validation report.

### Milestone

- M1.1 Integrated hardware platform available for modelling and data collection.

## WP2 — Digital Twin, Modelling, and Simulation Framework

Period: Mo4–12
Objective: Build a computational framework for modelling, simulation, and controller development.

### Tasks

- T2.1 Develop digital twin in PyDrake.

- T2.2 Develop digital twin in Isaac Sim.

- T2.3 Implement IK, inverse dynamics, static optimisation, and stiffness estimation pipeline.

- T2.4 Build weak-stiffness manipulator and exo-informed simulation framework.

- T2.5 Validate consistency between hardware and simulation.

### Deliverables

- D2.1 PyDrake digital twin implemented.

- D2.2 Isaac Sim digital twin implemented.

- D2.3 Musculoskeletal dynamics and endpoint stiffness pipeline implemented.

- D2.4 Exo–manipulator simulation framework for stiffness transfer.

- D2.5 Simulation validation report.

### Milestone

- M2.1 Multi-platform digital twin established for learning and control.

## WP3 — EMG, Human Reference Modelling, and Stiffness Transfer

Period: Mo6–15
Objective: Generate and use human-inspired neuromuscular reference signals for stiffness modulation.

### Tasks

- T3.1 Develop synthetic EMG generation pipeline.

- T3.2 Build musculoskeletal ground-truth pipeline linking trajectory, torque, activation, and stiffness.

- T3.3 Define tele-impedance-inspired mapping from human EMG/co-contraction to robot/exosuit stiffness.

- T3.4 Fit surrogate stiffness models for real-time implementation.

- T3.5 Prepare human-reference datasets for RL and controller development.

### Deliverables

- D3.1 Synthetic EMG generation pipeline completed.

- D3.2 Joint and endpoint stiffness estimation framework completed.

- D3.3 Tele-impedance / co-contraction transfer model defined.

- D3.4 Real-time stiffness surrogate model fitted.

- D3.5 Human-inspired reference dataset for control and learning.

### Milestone

- M3.1 Human-inspired stiffness-transfer framework established.

## WP4 — Learning-Based Control and Policy Development

Period: Mo10–20
Objective: Develop controllers and learning policies for stiffness-modulated manipulation.

### Tasks

- T4.1 Implement computed-torque baseline controller.

- T4.2 Design exosuit-mediated stiffness control architecture.

- T4.3 Train RL / imitation learning policy in digital twin.

- T4.4 Compare exo-off vs exo-on vs learned-policy performance.

- T4.5 Prepare deployment framework for real-robot validation.

### Deliverables

- D4.1 Baseline CT controller implemented.

- D4.2 Stiffness-control framework implemented in simulation.

- D4.3 RL / imitation learning policy trained in digital twin.

- D4.4 Controller benchmarking report.

- D4.5 Deployment-ready controller package.

### Milestone

- M4.1 Learned stiffness controller ready for real-system testing.

## WP5 — Human Experimentation, Ethics, and Validation

Period: Mo8–24
Objective: Validate the framework through human and robot experiments.

### Tasks

- T5.1 Prepare ethics application and safety documentation.

- T5.2 Finalise participant protocol for ball-in-cup disturbance adaptation experiment.

- T5.3 Conduct healthy-participant experiments.

- T5.4 Use collected data for validation of EMG, stiffness, and disturbance-recovery models.

- T5.5 Conduct real-robot validation with learned stiffness policy.

- T5.6 Prepare rehabilitation-oriented interpretation and future patient-study pathway.

### Deliverables

- D5.1 Ethics application package.

- D5.2 Final human experimental protocol.

- D5.3 Healthy-participant dataset.

- D5.4 Human vs robot validation report.

- D5.5 Real-system evaluation report.

- D5.6 Journal manuscript submission package.

### Milestone

- M5.1 Ethics approval obtained.

- M5.2 Human and robot validation completed.

## WP6 — Dissemination, Documentation, and Research Translation

Period: Mo1–24
Objective: Ensure outputs are documented, published, and positioned for future rehabilitation impact.

### Tasks

- T6.1 Maintain code/documentation pipeline.

- T6.2 Prepare conference and journal publications.

- T6.3 Release reproducible simulation/model documentation.

- T6.4 Build pathway toward rehabilitation and clinical translation.

- T6.5 Support future funding and follow-on proposals.

### Deliverables

- D6.1 Code and documentation repository.

- D6.2 Conference paper submission.

- D6.3 Journal paper submission.

- D6.4 Translation/future-clinical roadmap.

- D6.5 Follow-on funding concept note.

### Milestone

- M6.1 Publication and translation package in place.

# Small comparison table: revised WP deliverables vs completed work

You asked for a small comparison table. Here is a concise one.

| Revised WP | Main deliverables | Current status | Rough completion |
| --- | --- | --- | --- |
| WP1 Hardware platform | Manipulator, exosuit hardware, rail setup, sensing integration | Manipulator and exosuit hardware built; rail platform concept well developed; sensing/calibration framework partly defined | 75–80% |
| WP2 Digital twin & modelling | PyDrake twin, Isaac Sim twin, IK/ID/stiffness pipeline | PyDrake and Isaac Sim twins built; modelling and stiffness pipeline implemented | 85–90% |
| WP3 EMG & stiffness transfer | Synthetic EMG, stiffness estimation, tele-impedance mapping, surrogate model | Synthetic EMG done; stiffness pipeline done; transfer framework largely defined | 80–85% |
| WP4 Learning-based control | CT controller, stiffness control, RL policy, deployment framework | CT framework and RL setup defined; policy training/deployment partly ongoing | 50–60% |
| WP5 Human experiments & validation | Ethics, participant protocol, data collection, validation | Ethics in preparation; protocol developed; participant testing not yet started | 25–35% |
| WP6 Dissemination & translation | Papers, documentation, roadmap | Documentation strong; paper planning active; major submission still pending | 40–50% |

# Rough overall percentage of proposal completed

A reasonable estimate is:

## Overall completion: ~60–65%

That estimate is defensible because:

- Hardware and simulation/model development are far advanced.

- Synthetic EMG and stiffness pipelines are largely complete.

- Learning/control is partially advanced.

- Human testing and final validation are still pending, and these are major remaining parts.

If you want a slightly more optimistic version for internal reporting, you could say:

Approximately 65% of the revised project has been completed, with the strongest progress in hardware development, digital twin modelling, musculoskeletal/EMG pipeline development, and stiffness-transfer framework design. The main remaining activities are ethics approval, human participant experiments, policy deployment, and final validation/publication.

# Short polished paragraph for your report

You can use this directly:

As the project has evolved beyond the original proposal structure, the work packages have been updated to reflect the present research direction, which now integrates manipulator and exosuit hardware, dual digital twins in PyDrake and Isaac Sim, musculoskeletal stiffness modelling, synthetic EMG generation, and a rail-based ball-in-cup human experiment. Relative to this revised WP structure, the project is approximately 60–65% complete. Progress is strongest in hardware development, modelling, simulation, and EMG/stiffness pipeline development, while the main remaining work concerns ethics approval, human participant testing, learning-based deployment, and final validation.

If you want, I can next turn this into either:

- a formal MSCA-style revised WP section, or

- a very compact one-page progress report table with tasks / deliverables / status / evidence / % complete.

Yes — here is a clean table showing when each item was originally meant to be delivered and how early / fast it has been delivered relative to the proposal timeline.

Assumption used: Month 1 = November 2025, so late May 2026 ≈ Month 7.

## Planned vs actual delivery speed table

| Item | Original proposal delivery month | Expected calendar month | Current actual status by May 2026 | Delivered by current month? | Delivery speed / comment |
| --- | --- | --- | --- | --- | --- |
| Preliminary actuator/material design (D1.1) | Mo3 | Jan 2026 | Hardware development progressed beyond initial design stage | Yes | Delivered on time or earlier |
| Testing rig / prototype / actuation setup (D1.2) | Mo4 | Feb 2026 | Core manipulator and exosuit hardware built | Yes | Delivered on time or earlier |
| Final FReSCMA / core stiffness-modulation hardware (D1.3) | Mo5 | Mar 2026 | Exosuit stiffness-modulation hardware built | Yes, approximately | Roughly on time |
| Leakage/load testing (D1.4) | Mo6 | Apr 2026 | Not clearly documented in current notes | Unclear | Cannot confirm yet |
| MoCap / characterization results (D1.5) | Mo7 | May 2026 | Platform and modelling advanced, but formal characterization output not clearly shown | Partly / unclear | About due now |
| Final WP1 testing (D1.6) | Mo8 | Jun 2026 | Hardware platform already integrated into broader workflow | Not yet formally due | Likely on track |
| Fully functional actuator milestone (M1.1) | Mo8 | Jun 2026 | Hardware built before Mo8 | Partly achieved | Slightly ahead of schedule |
| Complete model (D2.1) | Mo9 | Jul 2026 | Digital twins in PyDrake and Isaac Sim already built | Yes | About 2 months early |
| Direct modelling implementation (D2.2) | Mo10 | Aug 2026 | Modelling pipeline already implemented | Yes | About 3 months early |
| Harness and cuff / suit development (D2.3) | Mo12 | Oct 2026 | Exosuit hardware already built | Yes, at least partially | About 5 months early |
| Final CASREx suit (D2.4) | Mo14 | Dec 2026 | Partial system hardware exists, but final validated suit not yet fully shown | Partly | Advanced early, but not fully closed |
| Actuation/control box (D2.5) | Mo16 | Feb 2027 | Control architecture exists in simulation; hardware box not clearly confirmed | Partial | Conceptually ahead, hardware completion unclear |
| RL model (D3.1) | Mo19 | May 2027 | RL framework, reward structure, and training entry points already defined | Partial | Foundations about 12 months early |
| Controller (D3.2) | Mo21 | Jul 2027 | CT controller and stiffness-control framework already implemented in simulation | Partial | Foundations about 14 months early |
| Lab/pilot reports (D3.3–D3.5) | Mo24 | Oct 2027 | Ethics and protocol preparation underway; human studies not started | No | Not due yet |

## Simpler “speed” summary table

| Category | Originally due | Status by Mo7 | Speed |
| --- | --- | --- | --- |
| WP1 hardware build | Mo3–Mo8 | Mostly completed in core form | On time to slightly ahead |
| WP2 modelling | Mo8–Mo16 | Major parts already completed by Mo7 | ~2 to 9 months ahead |
| WP3 control foundations | Mo16–Mo21 | Framework already defined in simulation | ~9 to 14 months ahead in groundwork |
| WP5 human testing | Later stage | Ethics in preparation, testing not yet started | Not yet delivered, but not late |

## One-line interpretation

Hardware delivery is roughly on time to slightly ahead, while modelling and control-framework development have been delivered significantly faster than planned, in some cases several months early.

If you want, I can also make this into:

- a more polished Word-style table, or

- a 4-column compact table: Deliverable | Planned month | Actual month/status | Months ahead.