| Work Packages | Due | Status by Month 8 (June, 2026) | Speed |
| --- | --- | --- | --- |
| WP1 Hardware platform development and experimental setup | Mo 8 | Completed | Near expected level |
| WP2 Digital twin, modelling, and simulation framework | Mo 16 | Completed | Several months ahead with 228% efficiency. |
| WP3 learning-based model, control, and pilot study | Mo 24 | 50 % completed, writing ethics approval, then pilot study after approval. | Strongly ahead. |
| WP4 Researcher Training and Knowledge transfer | Mo 20 | Active and Progressing Well: - Selected for the competitive European Talent Academy 2026 to collaborate with TUM and Politecnico di Milano (Polimi). - Currently preparing three grant applications: (a) one NVIDIA Academic Grant, and (b) two Imperial Connect Fund proposals with TUM and Polimi. - Appointed as an Assistant Supervisor at the Dyson School. - Ongoing supervision of two Year 3 MEng students and one PhD student. - Delivered a lecture and supervised DESE 71002 Robotics Research Projects. - Reviewed Imperial Summer School lectures. - Delivered invited lectures. - Delivered departmental and robotics postgraduate seminars. - Conducted two online lecture and discussion sessions for the Morph’s Lab group. | Strongly ahead |
| WP5: Communication and dissemination | Mo 24 | Started: Ongoing plan for journal paper submission to IEEE Transactions on Robotics. | On track |
| WP6: Result exploitation and management activities | Mo 24 | Ongoing: - Project management and supervision responsibilities in place, - Found mentor for writing Schimdt AI fellowship, - Satisfactory Project review meeting with Thrish every week. | On track |

During the reporting period, I have delivered performance that exceeds the expected level across research, teaching, supervision, knowledge transfer, and academic development.

Research Progress and Delivery: I completed the hardware platform development and experimental setup on schedule and delivered the digital twin, modelling, and simulation framework several months ahead of plan with very high efficiency. I have also advanced the learning-based modelling and control activities significantly ahead of schedule, with ethics preparation and pilot study planning already in progress.

Teaching, Supervision, and Knowledge Transfer: In parallel, I have made sustained contributions to the department through teaching, supervision, and knowledge transfer. I was appointed as an Assistant Supervisor at the Dyson School and have provided supervision for two MEng students and one PhD student. I have delivered lectures and technical teaching in robotics, contributed to DESE 71002 Robotics Research Projects, and reviewed Imperial Summer School lectures. In addition, I have delivered invited, departmental, and postgraduate seminars, and conducted two online lecture and discussion sessions for the Morph’s Lab group.

External Recognition and Funding Development: My contributions have also been recognized externally through selection for the competitive European Talent Academy 2026, and I am actively expanding the future funding opportunities through multiple grant applications, including an NVIDIA Academic Grant and Imperial Connect Fund proposals with international collaborators with TUM and Politecnico di Milano (Polimi).

Project Management and Dissemination: I have additionally supported project management, weekly review processes, and dissemination planning, including preparation for journal submission to IEEE Transactions on Robotics. Taken together, these achievements reflect performance above expectations, strong institutional contribution, and growing international visibility, providing clear justification for a salary award.